## Progress_Updates
What has been done | What we would like to discuss next
Reviewed Himalayan publications and Scientist notes against the MVP direction. | Which local problems are highest priority for the scientist team?
Built a hosted decision-support MVP with public and admin/operator paths. | Which workflows are worth retaining or changing?
Added batch/grid publication, uncertainty cues, terrain masking, bulletin-style display, export/share/report flows. | Which outputs match existing operational practice?
Prepared scientist review and daily verification concepts. | What review fields and adjudication process would be acceptable?
Kept explainable Random Forest as the current baseline model. | Which features and evidence are locally trusted?
Studied Swiss NHESS/RAvaFcast methods and EnviDat package. | Which Swiss ideas translate and which do not?
Downloaded and validated Swiss RF1/RF2 data; reproduced an initial RF4 research signal. | When can team like a short technical review of this lane?
Prepared Himalayan partner evidence templates for stations, weather, snowpack, labels, events, terrain, SAR scenes, scientist reviews, and holdout evidence. | Which templates should be simplified before sharing?
Kept SAR/remote sensing as a shadow-gated research path. | Whether remote-sensing validation is a priority now or later.
Created a three-month exploration outline. | Whether to continue, narrow, pause, or stop.

## Research_Lessons
Reference | Lesson | How we used it | Boundary
Himalayan publications | Sparse data, terrain complexity, manual evidence, operational judgement matter. | MVP and evidence templates were aligned to these pressures. | Requires local scientist confirmation.
NHESS 2022 | Raw forecast labels differ from cleaner reviewed truth. | Himalayan label templates require provenance and review fields. | No D_tidy-equivalent evidence yet.
GMD 2024 RAvaFcast | Swiss automation uses staged RF, spatial interpolation, and aggregation. | Swiss reproduction lane and GPxyz readiness were prepared. | Swiss success does not validate Himalayas.
WMO impact-based warnings | Forecasts should support decisions and communicate uncertainty. | UI emphasizes evidence, uncertainty, and review, not black-box answers. | Not an official warning service.
FAIR principles | Data should be findable, source-linked, and reusable. | Partner templates use source refs, manifests, and checksums. | Templates await real data.

## Challenge_Map
Challenge | Current response | Scientist input needed
Sparse observations | Station metadata planning, batch forecast grids, GPxyz readiness checks. | Reliable stations and pilot regions.
Manual snowpack burden | Field-report and scientist-review workflows. | Locally trusted snowpack/profile variables.
Rare events and class imbalance | Rare-event-aware metrics and class-imbalance controls. | Acceptable false-alarm and missed-event tolerance.
Weak layers and memory | Snowpack/weak-layer evidence templates. | Local definitions and case-review practice.
Black-box trust | Explainable Random Forest baseline and reviewable evidence surfaces. | Preferred explanation and audit style.
Spatial-temporal warning needs | Map/time display and bulletin framing. | Warning-region and elevation-band policy.
Remote-sensing promise | Shadow-gated SAR candidate lane. | Whether local scene validation is feasible.

## Top_15_Features
Webapp prototype feature | What exists today | Future plan | Claim boundary
Public avalanche forecast workspace | Public route / presents a forecast map, bulletin-style summary, time controls, selected-cell details, share, export, and report workflows. | Convert the same workflow into a Himalayan pilot workspace after local evidence and region wiring pass. | Technical decision-support prototype, not official warning authority.
Published batch forecast artifacts | The website loads precomputed forecast artifacts instead of running heavy computation in the browser. Current proof geography is Colorado Rockies. | Publish Himalayan pilot artifacts only after partner data, validation, and release-gate approval. | Colorado live proof does not prove Himalayan accuracy.
20x20 grid and 72-hour review pattern | The current proof surface supports grid-cell forecast review and multi-hour navigation. | Extend to locally agreed Himalayan grid size, forecast windows, warning regions, and elevation bands. | Grid display is review evidence, not slope-specific safety advice.
EAWS-style experimental bulletin | The UI presents danger level, avalanche problem, critical elevation/aspect context, and peak-window style information. | Align bulletin fields with scientist-approved local terminology and warning-region policy. | Experimental framing only until approved by scientists.
Interactive map and time slider | Users can inspect map cells across forecast hours and see state changes over time. | Add Himalayan pilot bounds, local basemaps if needed, and region-specific map presets. | Map output must stay caveated until local validation is complete.
Cell-level risk inspection | Selected cells show risk level, probability, hazard, exposure, vulnerability, problem type, model versions, and driver context. | Add scientist-approved thresholds, local features, and disagreement notes from daily verification. | Cell output is a discussion artifact, not field instruction.
Terrain and snow/public eligibility masking | The app distinguishes masked or unavailable terrain from normal danger classes, reducing false low-risk messaging. | Tune terrain masks with Himalayan DEM, elevation, ATES/runout evidence, and local scientist review. | Masking reduces overconfidence but still needs local field validation.
Uncertainty and reduced-confidence cues | The UI surfaces confidence interval, uncertainty class, stale/partial/unavailable states, and reduced-confidence labels where data is weak. | Add calibrated uncertainty from local holdout results and scientist-vs-model disagreement metrics. | Uncertainty is a review signal, not a guarantee.
Weather summary and snowpack proxy context | The risk panel can show weather summary and proxy snowpack context when artifact fields exist. | Replace proxy-level evidence with partner-reviewed snowpack, weak-layer, SNOWPACK/HIM-STRAT-like features where available. | Current proxy context is not weak-layer validation.
Explainability and risk-driver display | The app can display TreeSHAP-style or fallback risk-driver explanations, with artifact-origin caveats. | Tie each live artifact to active explainability metadata and add scientist-facing model reasoning review. | Explanation path must be verified per artifact before claiming active TreeSHAP.
Historical events and field-report evidence | The app supports avalanche event context and field-report workflows, with governance before training use. | Use partner-confirmed Himalayan events and scientist-reviewed field observations as validation evidence. | Raw reports are evidence inputs, not automatic truth.
Shareable forecast links | Users can copy a link preserving region, forecast hour, selected cell, expert mode, and 3D view state. | Use controlled shared links for scientist review sessions and pilot-region walkthroughs. | Shared link proves review context, not scientific acceptance.
CSV and JSON forecast export | Forecast cells, probabilities, uncertainty fields, problem type, and selected evidence can be exported from loaded artifacts. | Extend exports into partner-review packets and audit-ready evidence bundles. | Export reflects loaded artifact fields only.
Admin/operator control and observability | /admin supports job controls, model status, source health, evaluation metrics, publication traces, and candidate workflow visibility. | Harden into a release-control cockpit with explicit promotion blocks, source-health attestations, and audit history. | Admin evidence does not equal production approval.
Scientist validation and daily verification lane | /scientist and /scientist/daily-verification support role-gated review, paired scientist-vs-model comparison, verdicts, notes, and exportable evidence. | Make this the core co-working workflow for Himalayan validation, including D_tidy-style label review, model-disagreement analysis, and release-gate signoff. | Scientist review informs decisions; it does not automatically retrain or promote models.
Suggested next step | Output expected
First scientist discussion | Confirm whether the prototype direction is worth exploring and which pilot region, if any, is suitable.
Partner evidence intake | Collect reviewed station, weather, snowpack, label, event, terrain, and holdout evidence using the partner templates.
Himalayan research validation | Run local validation only after evidence passes source, license, quality, and leakage checks.
Scientist co-working review | Use the scientist workspace and daily verification lane to classify errors, label quality, and model disagreement.
Release decision | Continue, narrow, pause, or stop based on measured local evidence and named scientist signoff.

## Current_State
Question | Current answer
Is the website live? | Yes, as a technical decision-support MVP.
Is it a Himalayan operational validation? | No. Reviewed Himalayan evidence is still required.
Is Swiss RAvaFcast studied? | Yes, partially reproduced as a research reference.
Is SAR operational? | No. SAR remains shadow-gated.
Is GPU part of public scoring? | No. GPU is for off-path candidate workflows.
Is the first ask a large data handover? | No. The first ask is only a review discussion.

## Proposed_Pilot_Plan
Timeframe | Possible focus | Decision point
Month 1 | Understand local evidence, source permissions, and pilot-region options. | Is there enough reviewed local evidence for a pilot?
Month 2 | Run a limited research validation using agreed data and scientist review. | Does the direction show enough signal to continue?
Month 3 | Review results, limitations, and next-stage scope. | Continue, narrow, pause, or stop.
Ask | Why
One review discussion | To learn whether the direction is useful before sending heavy materials.
One scientist point of contact | To avoid fragmented technical interpretation.
One data point of contact | To handle source provenance and permissions carefully.
One or two pilot-region ideas | To keep the scope concrete and respectful of local knowledge.
Validation guidance | To avoid imposing an external definition of truth.

## Technology_Stack
Technology / method | Role | Current interpretation
React + Vite + TypeScript | Web interface for map, bulletin, review, and admin surfaces. | Product surface.
Supabase | Database/auth/artifact support. | Operational data layer.
Python batch pipeline | Forecast and evidence artifact generation outside the browser. | Backend processing layer.
Random Forest | Interpretable baseline for tabular weather/terrain/snowpack features. | Current live baseline.
Calibration and chronological splits | Reduce misleading accuracy and probability overconfidence. | Validation discipline.
Modal / GPU | Off-path heavier training and SAR workflows. | Research/candidate only.
RAvaFcast-style RF4 + GPxyz + aggregation | Swiss reference direction. | Research lane awaiting local evidence.